## Slide 1
C O M P A N I O N T O C D A V 1 . 1
K8s Event Triage Platform
Project Status — Implementation Snapshot
Owner
Platform Engineering Team
Version
1.0 — Draft
Date
2026-04-28
Companion to
CDA v1.1

## Slide 2
A G E N D A
What we'll cover
#
S E C T I O N
CO N T E N TS
01
Executive Snapshot
State of every component
02
System Design
Components · topology · routing · skills · HITL
03
Component Status
HITL · A2A · LGTM · agentgateway · skills · memory
04
Architecture Decisions
14 key calls + rationale
05
Agent Cards
~20 agents · 5 grouped patterns
06
Open Work
Pending items + owners
Platform Engineering · Project Status v1.0 · 2026-04-28
2

## Slide 3
S E C T I O N 0 1
Executive Snapshot
Where every moving part is today
Platform Engineering · Project Status v1.0 · 2026-04-28
3

## Slide 4
S T A T E O F E V E R Y C O M P O N E N T ( 1 / 2 )
What's already in production
T H E M E
STAT E
D ETA I L
Event ingestion (Alloy
→
Event Hub
→
Argo Events)
PRO D U CT I O N
Three-tier pipeline tested e2e on
proxmox-k8s
Argo Workflows triage DAG
PRO D U CT I O N
parse-otlp
→
fan-out
→
A2A
→
GitLab + Teams
KAgent A2A protocol
PRO D U CT I O N
JSON-RPC 2.0 ·
message/send
· agent-as-tool proven
agentgateway (replaced LiteLLM)
PRO D U CT I O N
UAMI to Azure OpenAI · OTel native · MCP & A2A gateway
HITL Teams bot PoC
P O C D O N E
End-to-end proven · Istio VS+AuthZ ·
smoke-test.sh
GitLab ticketing
PRO D U CT I O N
Direct REST today · MCP migration on roadmap
Specialist agent roster
P H A S E 2
11 namespace agents deployed · ~20 planned
Skills (kagent 0.8.0+)
S PA RS E
Mechanism deployed · library grows via learning loop
Platform Engineering · Project Status v1.0 · 2026-04-28
4

## Slide 5
S T A T E O F E V E R Y C O M P O N E N T ( 2 / 2 )
What's designed · in flight · future
T H E M E
STAT E
D ETA I L
Memory (pgvector backend)
I N F L I G H T
pgvector deployed ·
load_memory
wiring per-agent
Full A2A
→
HITL demo
I N F L I G H T
Joining Suspend
→
Adaptive Card
→
callback to specialist agents
Round-robin GitLab assignment
D ES I G N E D
Needs dedicated GitLab project + roster ConfigMap
Managed LGTM integration
D ES I G N E D
managed-lgtm-integration/
· pending platform-team Q&A
GitLab MCP integration
F U T U RE
Sequenced after HITL demo
ServiceNow / Azure DevOps MCP
F U T U RE
After GitLab MCP
gitops-remediation-agent
build
F U T U RE
After GitLab MCP
Real Teams Bot (replace Logic App)
F U T U RE
App registration + Bot Framework
Platform Engineering · Project Status v1.0 · 2026-04-28
5

## Slide 6
H E A D L I N E N U M B E R S
The shape of the thing
M ET R I C
VALU E
W H AT I T M E A N S
Agents
~20
Specialist agents · 11 deployed · 9 planned
Triage time
~60s
Event
→
diagnosis · vs. 30–60 min manual
Tiers
3
critical · warnings · infra · per consumer group
Dedup layers
3
Alloy · Sensor · Script TTL
Notification surface
2
GitLab issues · Teams Adaptive Cards
Cluster coverage
N+1
One management cluster · N worker clusters
Goal state: zero unresolved events — every K8s warning either auto-resolved by an agent or round-robin assigned to a human within minutes.
Platform Engineering · Project Status v1.0 · 2026-04-28
6

## Slide 7
S E C T I O N 0 2
System Design
Topology · routing · skills · output
Platform Engineering · Project Status v1.0 · 2026-04-28
7

## Slide 8
W H A T W E ' R E B U I L D I N G
AI-driven triage for Kubernetes warning events
A management cluster watches N worker clusters. When a K8s warning event fires, it flows through Argo Events
→
Argo
Workflows, gets dispatched to a specialist kagent agent that diagnoses the root cause via LLM, and the result becomes a
GitLab issue + Teams Adaptive Card. Write actions are gated by a Human-in-the-Loop approval before any cluster change.
COMPONENT
RO L E
Alloy
Per-cluster log/metric/event collector — forwards K8s warnings to Event Hub
Azure Event Hub
Cross-cluster event bus — Kafka-protocol, SAS-authenticated
Argo Events
EventBus (NATS) · EventSource (Kafka consumer) · per-tier Sensors
Argo Workflows
Triage DAG —
parse-otlp
→
fan-out
→
A2A
→
output
kagent
Specialist agent runtime — system prompt + skills + memory + tools
agentgateway
LLM proxy + MCP & A2A gateway · UAMI to Azure OpenAI · OTel native
AKS-MCP
Cross-cluster
kubectl
for the agents · UAMI / workload identity
HITL gate
Teams Adaptive Card via Logic App · Istio HMAC-verified callback
GitLab + Teams
Output surfaces — ticket destination + notifications
Platform Engineering · Project Status v1.0 · 2026-04-28
8

## Slide 9
M G M T C L U S T E R O R C H E S T R A T I N G W O R K E R S
Brain in the centre, eyes everywhere
MANAGEMENT CLUSTER
WORKER CLUSTERS (1..N)
Argo Events
EventBus · EventSource
Sensors per tier
Argo Workflows
k8s-triage-critical
warnings · infra
kagent system agents
infra · network · cost
observability · incident · compliance
gitops-remediation-agent
(future)
agentgateway
LLM proxy · MCP & A2A gateway
UAMI · OTel · guardrails
AKS-MCP
UAMI cross-cluster kubectl
Azure OpenAI
via UAMI / workload identity
Azure Event Hub
topics:
k8s-events · alerts
Alloy
events · logs · metrics · traces
Worker-local kagent
specialists
cert-manager · kyverno · kro
external-secrets · monitoring
App + system namespaces
generates K8s warning events
Worker K8s API server
Managed LGTM
Mimir · Loki · Tempo
Kafka/TLS
SAS Send
Kafka/TLS
SAS Listen
A2A JSON-RPC
UAMI · workload identity
UAMI
remote_write
loki.write · OTLP
Platform Engineering · Project Status v1.0 · 2026-04-28
9

## Slide 10
W H Y S P L I T M G M T V S W O R K E R
Different concerns, different blast radius
CONCERN
M A N AG E M E N T C L U S T E R
W O R K E R C L U S T E R
Cross-cluster
orchestration
Yes — AKS-MCP, multi-cluster routing
No — only sees self
System namespaces of
interest
argo
,
argo-events
,
kagent
,
agentgateway-
system
,
aks-mcp
cert-manager
,
kyverno
,
kro
,
external-secrets
,
monitoring
,
istio-system
,
flux-system
Triage location
Aggregates events from N workers
Local triage when EventHub round-trip is unnecessary
LLM access
Yes (via agentgateway)
Yes (via agentgateway, mgmt or local)
Latency
Slower — round-trip via Event Hub
Faster — local A2A
Worker-local triage shortens loops from seconds to milliseconds for namespaces that don't need cross-
cluster context (cert-manager, kyverno, kro etc.).
Platform Engineering · Project Status v1.0 · 2026-04-28
10

## Slide 11
N A M E S P A C E
→
A G E N T R O U T I N G
Two ConfigMaps drive the dispatch
Event arrives ─
parse-otlp extracts: namespace, reason
│
▼
Reason match? (Evicted, NodeNotReady, FailedMount, …)
YES → reason-route agent
NO → namespace-route agent
│
└── No match → sre-triage-agent (default)
│
▼
Workflow calls A2A: POST /api/a2a/kagent/<agent>/
│
▼
Agent loads:
• System prompt (in CRD)
• Skills (mounted /skills via skills-init)
• Memory (load_memory · pgvector — when re-enabled)
• Tools (kagent-tool-server via MCP)
│
▼
Diagnosis JSON returned to workflow
Routing config:
eventhub-otlp-pipeline/tier-critical/agent-routing.yaml
Platform Engineering · Project Status v1.0 · 2026-04-28
11

## Slide 12
S K I L L S · C O N T E X T · M E M O R Y
How agents pick up domain knowledge
LAYE R
S O U RC E
LOADED
WHEN
M EC H AN IS M
System prompt
Agent.spec.declarative.systemMessage
Pod start
Inline in CRD
A2A skill metadata
a2aConfig.skills
Pod start
Discovery / catalog only — not executed
Executable skills
spec.skills.gitRefs
or OCI
Pod start
skills-init
initContainer clones to
emptyDir
at
/skills
Tools
spec.declarative.tools
(MCP)
Per-request
RemoteMCPServer or Service · agentgateway can be central MCP
gateway
Memory
spec.declarative.memory
(when re-
enabled)
Per-request
load_memory(query)
·
save_memory(text)
· pgvector
Prompt template
data
promptTemplate.dataSources
Per-request
ConfigMap-backed builtins + per-namespace overrides
Critical naming rule:
spec.skills
(executable bundles)
≠
a2aConfig.skills
(metadata only).
Platform Engineering · Project Status v1.0 · 2026-04-28
12

## Slide 13
P E R - R E Q U E S T T R I A G E F L O W
Event
→
routing
→
agent
→
diagnosis
→
output
kagent agent pod (per-request)
K8s Warning Event
type=Warning
Alloy
kubernetes_events
Azure Event Hub
topic: k8s-events
EventSource
Kafka consumer
Sensor
rate-limited
parse-otlp
extract ns + reason
Router
namespace · reason
else default
namespace-routes
ConfigMap
reason-routes
ConfigMap
A2A POST
/api/a2a/kagent/<agent>/
System prompt + skills
/skills mounted
load_memory
→
pgvector
MCP tools
kagent-tool-server
AKS-MCP
LLM call
→
agentgateway
→
Azure OpenAI
Diagnosis JSON
Issue · Cause · Fix · Risk
Severity router
critical
→
HITL
warnings
→
direct
save_memory
incident summary
HITL gate
writes / remediation
Direct ticket
read-only triage
GitLab issue
round-robin assigned
Teams card
Adaptive Card
Platform Engineering · Project Status v1.0 · 2026-04-28
13

## Slide 14
O U T P U T V I A T E A M S H I T L
Approve · Reject · Edit — gate before any write
Triage agent
diagnosis + suggested fix
Workflow Suspend
paused · awaits callback
Teams Adaptive Card
via Logic App webhook
Approve
Reject
Edit
HMAC callback
POST + workflow token
Resume
approved=false
Re-prompt agent
human-modified text
Istio VS + AuthZ
HMAC verify
Argo Events webhook
EventSource on resume
Sensor resumes
approved=true
Remediation agent
controlled patch / scale
Verify
resource recovered
Ticket only
no remediation
GitLab issue updated
with outcome + resolution
back to triage
Platform Engineering · Project Status v1.0 · 2026-04-28
14

## Slide 15
T I C K E T I N G I N T E G R A T I O N S
Where triage lands
I N T E G RAT I O N
STAT U S
M EC H AN IS M
U S E C A S E
GitLab (REST API today)
PRO D U CT I O N
Direct API · workflow step
Default ticket destination · round-robin assignment
Microsoft Teams
PRO D U CT I O N
Logic App webhook
Adaptive Card notifications · HITL surface
GitLab MCP
F U T U RE
gitlab-mcp-server
Replace REST calls with MCP for richer ticket interactions
ServiceNow MCP
F U T U RE
servicenow-mcp
Enterprise incident · severity mapping · escalation chains
Azure DevOps MCP
F U T U RE
ado-mcp
Work item creation in Boards
All three MCPs sequenced after the full A2A
→
HITL demo lands. The incident-agent will select target(s)
by severity + namespace ownership when MCPs are wired.
Platform Engineering · Project Status v1.0 · 2026-04-28
15

## Slide 16
S E C T I O N 0 3
Component Status
Six pillars · where each one is
Platform Engineering · Project Status v1.0 · 2026-04-28
16

## Slide 17
H U M A N - I N - T H E - L O O P ( H I T L )
Workflow + Teams PoC done · A2A integration in
flight
E L E M E N T
STAT U S
Teams Adaptive Card payload via Logic App
PRO D U CT I O N
Argo Events webhook EventSource (callback)
PRO D U CT I O N
Istio VirtualService + AuthorizationPolicy (HMAC)
PRO D U CT I O N
Workflow
Suspend
→
Adaptive Card
→
resume
P O C D O N E
Mock Teams bot (stand-in until real bot lands)
P O C D O N E
Full A2A
→
HITL demo (specialist agents)
I N F L I G H T
Real Teams bot (replacing Logic App)
F U T U RE
Current focus: join the proven gate to specialist-agent A2A so a triage agent's suggested remediation can suspend, surface in Teams, and
resume on approval.
Platform Engineering · Project Status v1.0 · 2026-04-28
17

## Slide 18
A G E N T - T O - A G E N T ( A 2 A ) P R O T O C O L
JSON-RPC 2.0 with sharp edges
POST /api/a2a/kagent/<agent>/
{ "jsonrpc": "2.0", "id": "...", "method": "message/send",
"params": { "message": { "role": "user",
"parts": [{"kind":"text","text":"..."}] } } }
C O M M O N G O T C H A
SYMPTOM
Missing trailing slash on URL
404 silent
Method
tasks/send
(old docs)
"method not supported"
parts
missing
"kind": "text"
parse error
Session API used for sending
403 even with right user
Agent-as-tool pattern: kagent supports
tools: [{type: Agent, agent: {name, namespace}}]
natively. Proven March 2026 with the Kimi
coordinator (6/6 consecutive tool calls including a revision loop). Same path:
cert-manager-agent
→
gitops-remediation-agent
.
Platform Engineering · Project Status v1.0 · 2026-04-28
18

## Slide 19
M A N A G E D L G T M I N T E G R A T I O N
Alloy is the only handle — bidirectional
D I R E C T I O N
PATT E RN
COMPONENT
Push metrics
ServiceMonitor / PodMonitor
→
remote_write
prometheus.operator.*
→
prometheus.remote_write
Push logs
Pod logs + K8s events
loki.source.kubernetes
+
loki.source.kubernetes_events
Push traces
OTLP receiver
→
Tempo
otelcol.receiver.otlp
→
otelcol.exporter.otlp
Provision rules
PrometheusRule + LokiRule CRDs
→
managed Ruler
mimir.rules.kubernetes
+
loki.rules.kubernetes
Loop alerts back
AM webhook
→
Kafka
→
Event Hub
loki.source.api
→
otelcol.exporter.kafka
Agent anomalies
Recording-rule baselines + z-score / cohort
LogQL loop detection
Triage prompt enrichment
Workflow queries Mimir/Loki at triage-time
Splices context into KAgent prompt
D ES I G N E D
· Pending answers from platform team on Q1–Q14 · `aks-mgmt-stack/k8s-event-
triage/managed-lgtm-integration/`
Platform Engineering · Project Status v1.0 · 2026-04-28
19

## Slide 20
A G E N T G AT E WAY
LiteLLM replaced · agentgateway is current
state
✓
Migration complete. All agents route LLM, MCP, and A2A traffic through agentgateway. LiteLLM removed. PostgreSQL retained for kagent
memory.
W H Y W E M O V E D
W H AT S TAY E D
UAMI / workload identity to Azure OpenAI — no keys to rotate
kagent Agent CRDs — only ModelConfig
baseUrl
changed
OTel native —
agentgateway_gen_ai_*
token + latency metrics
A2A protocol — same JSON-RPC 2.0 contract
MCP gateway for centralised auth + federation
Argo Workflows DAGs — no change at all
A2A gateway for inter-agent routing + auth
PostgreSQL — retained for kagent memory
Per-route budgets + guardrails (regex / moderation / custom webhooks)
Platform Engineering · Project Status v1.0 · 2026-04-28
20

## Slide 21
S K I L L S M E C H A N I S M
Git-versioned, mounted via initContainer
Agent CRD spec.skills.gitRefs:
- url: https://github.com/your-org/your-skills-repo.git
ref: main
path: skills/cert-diagnostics
name: cert-diagnostics
│
▼
kagent injects "skills-init" initContainer
│
▼
Clones repos to emptyDir at /skills
│
▼
Main agent container mounts /skills read-only
Discovers skills via SKILL.md frontmatter
Executes scripts via built-in BashTool (sandboxed)
S TAT U S
Mechanism deployed and proven · library currently shallow
G R O W T H
Driven by the learning loop — every triaged ticket closes only when an agent skill is updated
Platform Engineering · Project Status v1.0 · 2026-04-28
21

## Slide 22
M E M O R Y S T A T U S
Designed · backend ready · integration in flight
In flight — pgvector deployed ·
load_memory
/
save_memory
designed · wiring into specialist agents alongside the A2A
→
HITL demo.
E L E M E N T
STAT U S
PostgreSQL + pgvector backend
D E PLOYE D
Embedding ModelConfig
D ES I G N E D
· separate from inference
load_memory
/
save_memory
tools
W I R I N G
per-agent
Memory + A2A design doc
DONE
Cross-incident pattern matching
D ES I G N E D
· keys:
event_reason
+
namespace
pgvectorscale upgrade path
O PT I O N A L
for StreamingDiskANN
Goal: agents check past incidents before re-investigating · "Seen before — incident #142, ACME fix worked" · 90-day TTL.
Platform Engineering · Project Status v1.0 · 2026-04-28
22

## Slide 23
S E C T I O N 0 4
Architecture Decisions
14 calls that shaped the design
Platform Engineering · Project Status v1.0 · 2026-04-28
23

## Slide 24
D E C I S I O N S 1 – 7
Specialisation, safety, contracts
#
D E C I S I O N
RAT I O N A L E
1
Specialist agents per namespace, not generalist
Smaller models hallucinate when omniscient · focused prompts win
2
Read-only by default · write only via promotion
Blast radius is the hard control · RBAC-enforced not prompt-enforced
3
Namespace anchoring (
CRITICAL: use exact namespace "X"
)
Empirical fix for Qwen 14B typos · belt-and-braces alongside Kyverno
4
A2A as the inter-agent contract
Standardised JSON-RPC · kagent native · agentgateway-routable
5
No
kubectl edit
from agents —
patch
/
apply
only
Interactive editors via MCP break ·
patch
is deterministic + auditable
6
GitOps remediation via MR, not direct cluster writes
Agent never
kubectl apply
s · opens MR · Flux applies · auditable, reversible
7
Triage agent
≠
remediation agent
Two CRDs, two SAs, two RBAC levels · never an upgrade in place
Platform Engineering · Project Status v1.0 · 2026-04-28
24

## Slide 25
D E C I S I O N S 8 – 1 4
Operations, gates, scaling
#
D E C I S I O N
RAT I O N A L E
8
HITL gate before any write action
Approve/Reject/Edit · auto-graduates to no-gate after N successes
9
Worker-local triage where possible
Eliminates Event Hub round-trip for self-contained namespaces
10
Round-robin GitLab assignment, no namespace
ownership
Builds breadth · visible at standups via Kanban
11
Skills are git-versioned, not in-line in CRDs
gitRefs
· skills library reviewable in PRs · CRD stays small
12
Agent prompts committed to Git
systemMessage
is a code artefact · changes go through PR review
13
3-layer dedup (Alloy / Sensor rate / script TTL)
Single layer brittle under storms · three layers means one can fail
14
agentgateway as single LLM exit point
One place for token tracking, guardrails, UAMI auth, OTel · agents don't know about Azure
OpenAI directly
Platform Engineering · Project Status v1.0 · 2026-04-28
25

## Slide 26
S E C T I O N 0 5
Agent Cards
~20 agents · 5 grouped patterns
Platform Engineering · Project Status v1.0 · 2026-04-28
26

## Slide 27
C O M M O N C A R D F I E L D S
Shared across all cards (unless flagged)
F I E L D
C O M M O N VA L U E
Process
Receive A2A
message/send
→
load skills + memory
→
call MCP tools
→
summarise
→
return JSON-RPC result. Optional A2A
call to
gitops-remediation-agent
for fixes.
Communication
Inbound: A2A from Argo Workflow. Outbound: A2A to other agents · MCP to
kagent-tool-server
,
aks-mcp
,
gitlab-mcp-
server
,
git-mcp-server
.
Tools (read)
k8s_get_resources
·
k8s_describe_resource
·
k8s_get_pod_logs
·
k8s_get_events
·
k8s_get_resource_yaml
Tools (write — remediation
tier only)
k8s_patch_resource
·
k8s_apply_manifest
·
k8s_delete_resource
·
k8s_label_resource
·
k8s_annotate_resource
·
k8s_execute_command
Knowledge
System prompt +
/skills
git bundle + (when enabled) pgvector memory +
kagent-builtin-prompts
ConfigMap
Evaluation
Output schema enforced (Issue/Affected/Root Cause/Remediation/Risk/Verification) · workflow grades fields and rejects
malformed
Security
Read-only RBAC default · write via explicit RoleBinding to specific namespaces · UAMI scope per cluster · prompt constraints
Model routing
All
→
agentgateway
→
Azure OpenAI (UAMI) or local vLLM · same
default-model-config
Platform Engineering · Project Status v1.0 · 2026-04-28
27

## Slide 28
C A R D A — T R I A G E S P E C I A L I S T
The dominant pattern (covers ~20 agents)
P R O C E S S
Reactive — invoked by workflow on K8s Warning event. Optionally proactive via CronWorkflow
(compliance, cost, security).
U S E R P E R S O N A
SRE / Platform Engineer responding to a triage notification — wants structured diagnosis + ranked
remediation + exact kubectl commands.
P R O B L E M
Domain-specific K8s failures hit a namespace · on-call lacks deep specialist knowledge · agent
collapses 30–60 min into seconds.
R O L E
Read-only investigator + remediation suggester. Writes nothing. Returns analysis JSON to the workflow.
Applies to: cert-manager · kyverno · kro · external-secrets · reloader · flux-system · gatekeeper-system ·
istio-ingress · istio-system · kube-system · dns · database · observability · cost · change · network ·
storage · infra · security · compliance.
Platform Engineering · Project Status v1.0 · 2026-04-28
28

## Slide 29
C A R D A — S P E C I A L I S T S K I L L S
What lives in
/skills/<agent>/
AGENT
S K I L L S B U N D L E
cert-manager-agent
cert-diagnostics
· ACME challenge inspection · issuer status · expiry scans
network-agent
cni-health-probe
·
ingress-backend-walker
·
istio-config-analyse
storage-agent
pvc-binding-trace
·
longhorn-volume-health
·
csi-driver-probe
infra-agent
node-condition-decoder
·
kubelet-log-grep
·
inotify-pressure-check
security-agent
pss-violation-decoder
·
falco-event-correlator
·
rbac-audit
cost-agent
right-size-recommender
·
idle-resource-finder
·
node-utilisation-report
compliance-agent
label-compliance-scan
·
quota-coverage-scan
·
network-policy-coverage
observability-agent
prometheus-target-health
·
loki-stream-audit
·
cardinality-explorer
Full per-agent definitions:
aks-mgmt-stack/k8s-event-triage/AGENT-ROSTER.md
Platform Engineering · Project Status v1.0 · 2026-04-28
29

## Slide 30
C A R D B — R E M E D I A T I O N A G E N T
Limited write · gated by HITL approval
P R O C E S S
Invoked only after HITL approval. Receives diagnosis + approval token. Executes recommended kubectl
actions in a controlled subset.
A L L O W E D A C T I O N S
patch
·
scale
·
restart
·
label/annotate
F O R B I D D E N
Delete CRDs · delete PVCs with data · restart all replicas at once · anything outside approved
namespace
S E C U R I T Y
Approval token verified against workflow HMAC · replay protection · action whitelist enforced server-side
· failures escalate, never retry
Applies to:
sre-remediation-agent
. All writes go through GitOps where possible · direct cluster writes
only for break-glass.
Platform Engineering · Project Status v1.0 · 2026-04-28
30

## Slide 31
C A R D C — G I T O P S R E M E D I A T I O N A G E N T
Future · branch + commit + MR · never
kubectl
apply
Future work — sequenced after the A2A
→
HITL demo lands
Concept proven via the Kimi 6/6 A2A pattern · build starts once GitLab MCP integration begins.
P R O C E S S
Receives A2A call from triage agent describing needed config change. Clones GitOps repo · branch · diff
· commit · MR. Never pushes to main.
U S E R P E R S O N A
SRE reviewing the MR — wants clean single-purpose diff with agent diagnosis as MR description and
GitLab triage issue linked.
T O O L S N E E D E D
git-mcp-server
(clone/checkout/commit/push/diff/file_*) ·
gitlab-mcp-server
with
requireApproval
on
create_merge_request
S A F E T Y C O N T R O L S ( P L A N N E D )
Bot account scoped to single GitOps project · MR title
[Auto-Fix]
· one change per MR · GPG-signed ·
detect-secrets pre-commit.
Platform Engineering · Project Status v1.0 · 2026-04-28
31

## Slide 32
C A R D D — S Y S T E M A G E N T S ( M G M T C L U S T E R )
Cluster-wide read · scheduled CronWorkflow
AGENT
S P E C I A L I S T S K I L L S
M OST LY
incident-agent
incident-correlator
·
severity-escalator
·
mttr-calculator
Process management
change-agent
rollout-watcher
·
canary-comparator
·
argocd-sync-checker
Deployment health
compliance-agent
weekly-compliance-report
·
audit-evidence-exporter
Reports + scorecards
cost-agent
weekly-cost-report
·
right-sizing-recommender
FinOps reports
observability-agent
monitoring-stack-health
·
cardinality-explosion-detector
Stack-of-stacks monitoring
User persona: Engineering leadership · FinOps · SRE management. Outputs: weekly reports as GitLab
issues · weekly Teams summaries · ServiceNow / Azure DevOps tickets when those MCPs land. RBAC:
read across all namespaces · incident-agent has write access to ticketing systems only.
Platform Engineering · Project Status v1.0 · 2026-04-28
32

## Slide 33
C A R D E — U K 8 S C E R T I F I C A T I O N A G E N T
Cluster-readiness certifier · agent-graded
verdict
Reuses
sre-triage-agent
· invoked from the
uk8s-certification-v2
RGD. Argo Workflow runs validation tasks
→
ConfigMap
aggregation
→
A2A handoff
→
strict-schema verdict back into Argo
outputs.parameters
.
AS P ECT
D ETA I L
Process
Per-workflow ConfigMap captures pass/fail counts ·
aggregate-certification
sums to CERTIFIED / FAILED ·
agent-triage
sends report
over A2A · agent returns
{severity, blast_radius, failed_checks[], first_remediation}
User
persona
Cluster operator certifying a new or updated cluster — wants a single gate plus an AI-graded list of what to fix first
Outputs
severity
(CRITICAL / WARNING / INFO / AGENT_UNAVAILABLE / PARSE_ERROR) and
verdict
as Argo output params — branchable by
Teams / exit hook / GitLab issue
Optional
gating
failOnCritical
(off by default) fails the workflow when severity = CRITICAL — upstream alerting fires
Source
infra-stack/kro-stack/definitions/uk8s-certification-v2.yaml
· doc:
UK8S-CERTIFICATION-V2.md
Platform Engineering · Project Status v1.0 · 2026-04-28
33

## Slide 34
S E C T I O N 0 6
Open Work
Pending items + ownership
Platform Engineering · Project Status v1.0 · 2026-04-28
34

## Slide 35
P E N D I N G I T E M S ( 1 / 2 )
In flight + designed
I T E M
STAT U S
OWNER
B LO C KE R
Full A2A
→
HITL demo
I N F L I G H T
Engineering
Wiring specialist agents into proven HITL gate
Memory integration into specialist agents
I N F L I G H T
Engineering
load_memory
/
save_memory
per-agent rollout
Specialist agents on workers
1 1 O F ~ 2 0
Engineering
→
SRE
Phase 3 of
ENGINEERING-ROLLOUT.md
Skills library expansion
CO N T I N U O US
All engineers
Driven by learning loop
LGTM integration deployment
D ES I G N E D
Engineering + Platform OPEN-QUESTIONS Q1–Q14
Round-robin GitLab assignment
D ES I G N E D
Engineering
Needs dedicated GitLab project + roster ConfigMap
Platform Engineering · Project Status v1.0 · 2026-04-28
35

## Slide 36
P E N D I N G I T E M S ( 2 / 2 )
Future · sequenced after HITL demo
I T E M
STAT U S
OWNER
B LO C KE R
GitLab MCP integration
F U T U RE
Engineering
After HITL demo · replaces direct REST calls
gitops-remediation-agent
build
F U T U RE
Engineering
After GitLab MCP lands
ServiceNow MCP integration
F U T U RE
TBD
After GitLab MCP
Azure DevOps MCP integration
F U T U RE
TBD
After ServiceNow MCP
Real Teams Bot (replace Logic App)
F U T U RE
TBD
App registration + Bot Framework deploy
Platform Engineering · Project Status v1.0 · 2026-04-28
36

## Slide 37
D O C U M E N T M A P
Where to go for the detail
DO CUMENT
P U RP OS E
docs/CDA-DESIGN-AUTHORITY.md
(v1.1)
Formal design authority position
docs/PROJECT-STATUS.md
Long-form companion to this deck
docs/CDA-SLIDES.md
(v1.1)
CDA as slides
docs/SAD-THREAT-MODEL.md
STRIDE threat model
docs/SAD-LOGGING-MONITORING-AUTH.md
Logging/monitoring/auth
docs/SAD-LOGGING-MONITORING-LLM.md
LLM governance
worker-cluster-bundle/SKILLS-AND-REMEDIATION.md
Skills loading mechanism
worker-cluster-bundle/MEMORY-AND-A2A-REMEDIATION-DESIGN.md
Memory + A2A remediation design
worker-cluster-bundle/AGENTGATEWAY-TRANSITION.md
LiteLLM
→
agentgateway migration
aks-mgmt-stack/k8s-event-triage/managed-lgtm-integration/
Managed LGTM design + agent anomalies
aks-mgmt-stack/k8s-event-triage/AGENT-ROSTER.md
Full per-agent specifications
Platform Engineering · Project Status v1.0 · 2026-04-28
37

## Slide 38
T H A N K Y O U
Questions?
Platform Engineering Team
Companion document:
docs/PROJECT-STATUS.md
Render:
marp PROJECT-STATUS-SLIDES.md --pdf --allow-local-files